## Slide 1: Robot Operating System Graphical User Interface
Colin Smith
Matthew Babiszewski
Jason Kerslake

## Slide 2: Robotics in Electrical Engineering
Currently use Robotic Operating System, or ROS for development of robots
Used for everything from teaching basic robotics all the way to advanced demonstrations, prototypes and real world applications
Open Source Computer Vision, or OpenCV library used for real-time image processing

## Slide 3: Requirements for the Application
Requested to develop a Graphical User Interface or GUI to aid software development & simplify the use of ROS
Easy to expand / modify application
Multi-platform (Microsoft Windows, GNU/Linux)
Deliverable code under an Open Source licence
Android counterpart if time permits

## Slide 4: Our Project
A GUI capable of performing basic robotic movement remotely, as well as showing a live video stream from the Robot
Video stream can have OpenCV filters applied

## Slide 5: But that’s not all!
The Application should allow ‘importing’ of modular code which allows for more functionality
Modular code should be easy to write, and capable of interfacing with the Video stream.

## Slide 6: Benefits
Ability to create more advanced functionality with a supporting GUI quickly and easily
Faster development time
Less knowledge required to operate ROS devices

## Slide 7: Limitations
Time – Finished before the 9th November
Language
Limited Budget
Licensing
Graphical Interface

## Slide 8: Critical Success Factors
Client Satisfaction
Functionality
Ease of Use
Quality of Coding and Documentation

## Slide 9: Scope
Functionality
Usability
Expandability
Security

## Slide 10: Project Plan
23rd July 2012 to 9th November 2012
Begin by researching ROS, OpenCV and modular application styles
Write Application prototypes, discussing them with Client and his decision on the final style
Develop Application
Documentation
Android Application if time permits
Page 10 of the Charter Document for more detailed infomation

## Slide 11: Deliverables
Document: ROS GUI Project Charter
Document: How to setup a distributed ROS Environment
Test Code: Modular Application Prototypes
Test Code: Research OpenCV
Deliverable: Streaming Video How-to
Code: Final Application
Documents: Tutorials / Developer documentation
Code: Android Application

## Slide 12: Documentation
In Tutorial or how-to form.
No standard yet
Will be drafted by the client, and test subjects who meet the target demographic to ensure documents are easily understood

## Slide 13: Communication Plan
Communication via Mobile Phone, Skype, Email and Facebook
GIT repository so we can access code from anywhere
Regular meetings once a week with both Supervisor and client

## Slide 14: Resource Requirements
Lab Space
Development Computers
Bandwidth
Android Device
Test Robot Device
Webcams

## Slide 15: Costs
Code | Description | Theoretical Cost | Actual Cost
Personnel | 3 x Graduate Developers @ 50kPA for 5 Weeks FTE, 1 x Supervisor / Senior Developer @ 120kPA for 20 Hours. | $15,576 | Not funded
Snacks and Beverages | High sugar and caffeine products. | $150 | Not funded
Development Computers | 2 x $1,250 computer systems | $2,500 | N/A (Provided)
Bandwidth | Up to $100 / Month over 3 months | $300 | N/A (Provided)
Android Device | Google Nexus 7 | $249 | $249
Webcams | 2 x GNU/Linux compatable Video Cameras for use during development @ $60 each | $120 | N/A (Provided)
Test Robot | Test robot to ensure application works as expected. Used for short periods of time. | Unknown | N/A (Provided)

## Slide 16: Risks and Know issues
Risk | Likelihood
Change of requirements in the project or features added along the life span of the project. | Likely
Absence of Supervisor / Client during meetings and project development. | Likely
Loss of sponsor due to redirection of UniSA and its resources. | Unlikely
Failure to meet schedule in a suitable time frame. | Likely
Different opinions on the final project design caused by group malfunction. | Likely
Project differs from clients expectations due to miscommunication. | Likely
Unable to test software on the robot at the correct time frame due to delays in target robot. | Unlikely
Project unable to work with the required robot nearing completion of the project. | Very Likely
Loss of team members due to unforeseen circumstances. | Unlikely

## Slide 17: Constraints
Software Dependencies
Time
Android Device
Software Licencing

## Slide 18: Assumptions
Assumed the Python wrappers
Not required to retrofit existing software
All Robotic Systems are GNU/Linux based
Users prior knowledge

## Slide 19: Interfaces with Other Projects
No direct external API – But modular functionality will exist.
All code will be well documented

## Slide 20: Communication
When / how often / how will we meet?
  Facebook, Skype, E-Mail, in person
  At least once a week independant of client meeting
Supervisor and Client communication
  Meet once a week with Client and Supervisor
Development Specific communication
  Via GIT check-ins / commits, Comments and E-Mail

## Slide 21: Organization
Steering Committee
  Dr. Russell Brinkworth (Project Owner) – School of Electrical and Information Engineering
  Dr. Ivan Lee (Project Supervisor)
Core Team
  Dr. Ivan Lee (Project Supervisor)
  Colin Smith (Team Lead, Programmer)
  Matthew Babiszewski (Programmer)
  Jason Kerslake (Programmer)

## Slide 22: Meeting Structure
L = Lead Role S = Supporting Role
Responsibility | Project Owner | Supervisor | Team Leader | Programmers
Ensure project plan is acceptable | L | S |  | 
Ensure that the core team is provided with support | S | L |  | 
Track progress of the project |  | S | L | S
Ensure Team Leader is supported throughout project |  |  | S | L
Ensure the team functions in a productive manor |  | S | L | S
Ensure tasks are completed on time |  | S | L | S

## Slide 23: Meeting Structure (Continued)
L = Lead Role S = Supporting Role
Responsibility | Project Owner | Supervisor | Team Leader | Programmers | Supporting Teams
Ensure final deliverable is complete and on time |  | S | L | S | 
Ensure project deliverables are what the client requested |  | S | L | S | 
Ensure code is to a good standard and quality |  |  | L | S | 
Ensure code is documented in an easy to read manor for final deliverable |  |  | L | S | 
Ensure final testing robot is adequate and on time. | L |  |  |  | S

## Slide 24: Progress Tracking
Weekly stand up meetings
  Used as a checkpoint to track the progress of the project.
Gantt chart
  Used to track actual due dates and milestones to ensure that the project is on schedule.

## Slide 25: Risk and Issue Management
Risk ID | Likelihood | Impact | Risk Level & Score | Mitigation Plan
1 | Likely | Minor | Low - 1 | As change of requirements is likely, a significant amount of slack time will be allocated. It is expected that any change in requirements will not be any more significant than slight modifications in application behavior.
2 | Likely | Moderate | Medium - 2 | Our Supervisor Dr. Ivan Lee has advised that he will be away from Week 9 onwards, however he has arranged a replacement to supervise the project and the team will have to get the new supervisor up to speed.
3 | Unlikely | Major | Medium - 2 | As the project is working for an internal branch of the University of South Australia, and functionality of the project expected to substantially benefit a course beginning next year, it is unlikely the sponsor will discontinue the project or cease communication as a body.
4 | Likely | Major | High - 3 | Failure to meet schedule will be prevented by good management and planning along with regular group meetings. The team will ensure that the time and checkpoint schedules are met by using a Gantt chart to track progress where slack is provided on the critical path. This will ensure that any problems or issues that are faced are able to be mitigated.

## Slide 26: Risk and Issue Management
Risk ID | Likelihood | Impact | Risk Level & Score | Mitigation Plan
5 | Likely | Minor | Low - 1 | Team work, strong lead and direction will be used as the mitigation plan and any members that are unhappy will be able to discuss any issues with the project supervisor.
6 | Likely | Moderate | Medium - 2 | The team will be using this document to gather specific requirements of this project and the requirements will be confirmed with Dr. Russell Brinkworth to help alleviate this risk.
7 | Unlikely | Moderate | Low - 1 | This risk should be minimal as Dr. Russell Brinkworth will ensure a robot is available at the time of need. As the software should be able to run on a range non specific devices and robots, this risk will be minimized.
8 | Very Likely | Major | Extreme - 4 | This risk will be mitigated by making sure we are on the right track with development and the robot specifications are known in advance or get the robot for the test phase sooner.
9 | Unlikely | Major | Medium - 2 | The remaining team members will have to pick up the slack as this risk won’t be able to be avoided if the team should lose a member and they will have to finish the work on time.

## Slide 27: Risk Matrix
< Impact >
< Likelihood >
Very Likely | Medium 2 | High 3 | Extreme 4
Likely | Low 1 | Medium 2 | High 3
Unlikely | Low 1 | Low 1 | Medium 2
 | Minor | Moderate | Major
Risk Score & Risk Level | Risk Impact
1 - Low | Risk is negligible. Mitigation Plan could avoid impact of risk or very unlikely chance of happening.
2 - Medium | Risk has a chance of happening and could cause setbacks in the project. Mitigation plans must ensure risk can be avoided as much as possible.
3 - High | Risk is highly possible and a mitigation plan must attempt to cover all potential undesired outcomes thoroughly.
4 - Extreme | Risk will definitely happen. The most extreme case. Mitigation Plan(s) will need to reduce these risks where possible or an alternate option should be discussed.

## Slide 28: Questions?